| Agenda Item 11 | EIHA 24/11/01-Annex.03 Original English |
| --- | --- |
| OSPAR Convention for the Protection of the Marine Environment of the North-East Atlantic |  |
| Meeting of the Environmental Impact of Human Activities Committee (EIHA) Madrid (Spain) and on-line: 15-19 April 2024 |  |

Paragraph 16 of this document was amended after OSPAR's Head of Delegation meeting on 16 May 2024.

Terms of Reference for the task group on deep-seabed mining 2024-2027

1.       	Background

1.       	There is an increasing demand for specific resources (manganese, copper, cobalt, nickel, lithium and silver along with rare earth elements and critical metals), due to growing populations, high-technology applications, increasing rarity of high-grade land-based deposits and the push towards adopting low carbon technologies to help meet climate change goals. Deep-seabed mining (DSM) has the potential to meet these growing mineral resource demands. However, there is a concern regarding our limited knowledge of deep-sea ecosystems and the potential impacts mining may have on deep sea biodiversity, habitats, fisheries and the carbon cycle.

2.       	Deep-sea resources of interest which occur within the OSPAR region include seafloor massive sulphide deposits within hydrothermal vent fields and areas that potentially contain rich deposits of polymetallic nodules (“nodules”) and cobalt-rich ferromanganese crusts (“crusts”).

3.       	Based on present knowledge, there are common impacts across all resource types, all with potential direct or indirect detrimental effects on biodiversity such as (not exhaustive):

• Loss of substrate;

• Changes to seabed integrity (due to compaction, removal of topmost sediments, changes in geochemical conditions, changes in topography);

• Operational suspended sediment and chemical plumes;

• Re-sedimentation from operational plume;

• Discharge plume;

• Increase in light;

• Increase in noise levels and potential vibration; and

• Release of sediment-bound or subsurface porewater toxic metals into the water column.

4.       	The above background is from OSPAR’s 2021 technical report available here, where further information on deep-seabed mining resources, technology, potential impacts and regulation along with the  global demand for minerals can be found.

5.       	OSPAR 2019 agreed to establish a task group in order to exchange information and positions related to deep-seabed mining; help Contracting Parties ensure that obligations under the OSPAR Convention are upheld; and review the MOU between OSPAR and the ISA to see if it remained fit for purpose. From 2019 to 2023 the task group has been led by the United Kingdom, and has reported its progress annually to EIHA.

6.       	In 2021 the task group completed its work on a first technical report (see above) and prepared a draft report on OSPAR measures applicable/relevant to DSM which led to a request to the Group of Jurists-Linguists (J/L) to give advice on OSPAR’s competence with regard to deep-seabed mining within the OSPAR maritime area. J/L adopted its advice following its meeting of 13 October 2022 (J/L (2) 2022 summary record, annex 1).

7.       	The task group is responsible for one of the tasks in the NEAES 2030 Implementation Plan, task S7.05.T3., reflecting the mandate given by OSPAR 2019.

2.       	Objectives

8.       	The objectives of the DSM task group are to promote the general and specific obligations under the OSPAR Convention and the strategic and operational objectives of the NEAES 2030 by:

- exchanging information and positions between OSPAR Contracting Parties related to DSM;

- helping Contracting Parties to ensure that their obligations under the OSPAR Convention are upheld when assessing and managing DSM activities;

- overseeing the implementation of the MOU between OSPAR and the ISA.

9.       	Relevant NEAES objectives include S5.04 and S5.05 (biodiversity), S7.01 (cumulative effects), S7.05 (new, emerging and increasing pressures), S8.01 (underwater noise) and S12.01 (carbon sequestration).

3.       	Scope of work

10.     	The scope of the task group includes all deep-seabed mining activities as follows:

•        	For areas beyond national jurisdiction: all activities of exploration for, and exploitation of, the resources of the Area (UNCLOS Article 1(3)), where the “Area” means the seabed and ocean floor and subsoil thereof, beyond the limits of national jurisdiction (UNCLOS Article 1(1)), and where “resources” means all solid, liquid or gaseous mineral resources in situ in the Area at or beneath the seabed, including polymetallic nodules (UNCLOS Article 133(a)).

•        	For areas within national jurisdiction: all activities of exploration for, and exploitation of, polymetallic nodules, polymetallic sulphides and polymetallic crusts.

11.     	In undertaking the scope of its work, in particular considering OSPAR measures applicable/relevant to DSM, the task group will follow the advice from J/L (J/L (2) 2022 summary record, annex 1) outlining OSPAR competency regarding DSM.

12. In undertaking the scope of its work, the group will take into consideration latest technical, scientific and policy developments.

4.       	Activities and deliverables

13.     	In the period 2024-2027 the task group will focus on:

- Assessing and better implementing the OSPAR-ISA MoU to ensure OSPAR objectives are promoted and achieved regarding DSM in the OSPAR Maritime Area, with the priority on the analysis of draft International Seabed Authority (ISA) regulations on exploitation and the Regional Environmental Management Plans (REMPs) within the ISA.

  - assess the extent to which the provisions in the MoU have been used and how effective they have been when they have been used (Q2/3 2024)

  - focus on identifying additional specific actions under the MoU focused around achieving OSPAR objectives in the OSPAR Maritime Area. (Q 3/4 2024)

  - Implementing the action plan developed above (Q1 2025 onwards)

- Redraft and finalise Paper 2: OSPAR measures applicable/relevant to DSM in light of J/L advice (J/L (2) 2022 summary record, annex 1). This paper will provide an overview of which OSPAR measures may be applicable/relevant to DSM (see document EIHA 21/07/11) (Q3 2024, considered by EIHA(2) 2024 ).

iii.       Potential drafting of Paper 3: Policy recommendations for OSPAR on DSM. If prepared, this document could include, for example, a set of recommendations on how best OSPAR could most appropriately engage with the International Seabed Authority (ISA) (not yet produced). If produced, this paper should take into account stakeholder views. The decision by EIHA on whether to action a third paper on policy recommendations will be based on the outcomes of paper 2 (Considered by task group and presented to EIHA at potential intersessional meeting of EIHA HoDs Q3 2024).

- OSPAR Science Agenda: the task group leads will make an initial filter of the OSA knowledge gaps identified in EIHA and the QSR 2023 of relevance to the task group, and the overarching knowledge gaps, to determine the most relevant knowledge gaps for monitoring, measures and research for their work. Based on the task group leads’ initial filter, the task group will:

  - determine whether the knowledge gaps are legitimate and identify, classify and prioritise the task group relevant knowledge gaps to be listed accordingly in the OSPAR Science Agenda;

  - For each knowledge gap, consider if the wording used is clear enough for an external audience, providing alternative text suggestions as required;

  - Where the NEAES column is blank, attempt to link the knowledge gap to a NEAES objective or implementation plan task. If this is difficult, consider whether the knowledge gap is a high priority;

  - Forward the results to the OSA task group leads, Lisette Enserink (lisette.enserink@rws.nl) and Marianne Olsen (marianne.olsen@miljodir.no), copying the Secretariat (Carole.Durussel@ospar.org).

5.               Working procedures

14.     	The DSM task group will meet twice a year (with ad-hoc meetings on specific issues where needed) and as far as possible will hold its meetings on-line.

15.     	The task group will report on an annual basis to EIHA on progress made and discuss any revisions of the ToR as necessary.

6.       	Co-convenor and Participants

16.     	The DSM task group will be convened by Ireland (Katherine Cronin) and Norway (Jan Stenløkk) and is open to all OSPAR Contracting Parties and Observers.